## jobs
Job ID | Job name | Job Release Date | Job Due Date | Job Priority
J1 | Rear shaft | 0 | 335 | 4
J2 | Main gear | 0 | 242 | 4
J3 | Secondary gear | 0 | 289 | 2
J4 | 3F-757 Housing | 0 | 460 | 2
J5 | 8H-1247 Seal support | 0 | 308 | 2
J6 | Rear shaft | 0 | 429 | 2
J7 | Main gear | 0 | 537 | 2
J8 | Secondary gear | 0 | 320 | 2
J9 | 3F-757 Housing | 0 | 303 | 1
J10 | 8H-1247 Seal support | 0 | 506 | 1

## machines
Machine ID | Machine Name
M1 | TW-01
M2 | TW-02
M3 | CNC-01
M4 | CNC-02
M5 | LC-01

## tasks
Task ID | Job ID | Task Name | Task Runtime | Machine ID | Predecessor Task ID
T1 | J1 | J1 Task 2 | 21 | M2
T2 | J1 | J1 Task 3 | 34 | M3 | T1
T3 | J1 | J1 Task 1 | 53 | M1 | T2
T4 | J1 | J1 Task 4 | 55 | M4 | T3
T5 | J1 | J1 Task 5 | 95 | M5 | T4
T6 | J2 | J2 Task 5 | 16 | M5
T7 | J2 | J2 Task 1 | 21 | M1 | T6
T8 | J2 | J2 Task 3 | 26 | M3 | T7
T9 | J2 | J2 Task 4 | 52 | M4 | T8
T10 | J2 | J2 Task 2 | 71 | M2 | T9
T11 | J3 | J3 Task 1 | 12 | M1
T12 | J3 | J3 Task 3 | 31 | M3 | T11
T13 | J3 | J3 Task 4 | 39 | M4 | T12
T14 | J3 | J3 Task 2 | 42 | M2 | T13
T15 | J3 | J3 Task 5 | 98 | M5 | T14
T16 | J4 | J4 Task 1 | 55 | M1
T17 | J4 | J4 Task 3 | 66 | M3 | T16
T18 | J4 | J4 Task 2 | 77 | M2 | T17
T19 | J4 | J4 Task 4 | 77 | M4 | T18
T20 | J4 | J4 Task 5 | 79 | M5 | T19
T21 | J5 | J5 Task 2 | 19 | M2
T22 | J5 | J5 Task 4 | 34 | M4 | T21
T23 | J5 | J5 Task 5 | 37 | M5 | T22
T24 | J5 | J5 Task 3 | 64 | M3 | T23
T25 | J5 | J5 Task 1 | 83 | M1 | T24
T26 | J6 | J6 Task 3 | 43 | M3
T27 | J6 | J6 Task 2 | 54 | M2 | T26
T28 | J6 | J6 Task 4 | 62 | M4 | T27
T29 | J6 | J6 Task 5 | 79 | M5 | T28
T30 | J6 | J6 Task 1 | 92 | M1 | T29
T31 | J7 | J7 Task 4 | 69 | M4
T32 | J7 | J7 Task 5 | 77 | M5 | T31
T33 | J7 | J7 Task 2 | 87 | M2 | T32
T34 | J7 | J7 Task 3 | 87 | M3 | T33
T35 | J7 | J7 Task 1 | 93 | M1 | T34
T36 | J8 | J8 Task 4 | 24 | M4
T37 | J8 | J8 Task 3 | 38 | M3 | T36
T38 | J8 | J8 Task 2 | 41 | M2 | T37
T39 | J8 | J8 Task 1 | 60 | M1 | T38
T40 | J8 | J8 Task 5 | 83 | M5 | T39
T41 | J9 | J9 Task 4 | 17 | M4
T42 | J9 | J9 Task 5 | 25 | M5 | T41
T43 | J9 | J9 Task 1 | 44 | M1 | T42
T44 | J9 | J9 Task 2 | 49 | M2 | T43
T45 | J9 | J9 Task 3 | 98 | M3 | T44
T46 | J10 | J10 Task 3 | 43 | M3
T47 | J10 | J10 Task 2 | 75 | M2 | T46
T48 | J10 | J10 Task 5 | 96 | M5 | T47
T49 | J10 | J10 Task 4 | 79 | M4 | T48
T50 | J10 | J10 Task 1 | 96 | M1 | T49