## machines
Machine ID | Machine Name | Machine Description | Machine Family
0 | TW-01 | Tig welding machine 1 | TW
1 | TW-02 | Tig welding machine 2 | TW
2 | CNC-01 | CNC machine 1 | CNC
3 | CNC-02 | CNC machine 2 | CNC
4 | LC-01 | Laser cutter 1 | LC

## orders
Order ID | Order Name | Customer ID
1 | Transmission Gears | 30150
2 | Airbus AOG bearings | 28014

## jobs
Job ID | Order ID | Job name | Job Quantity | Job Release Date | Job Due Date | Job Status | Job Priority | Job Comments
1 | 1 | Rear shaft |  | 0 | 335 | Accepted | 4
2 | 1 | Main gear |  | 0 | 242 | Accepted | 4
3 | 1 | Secondary gear |  | 0 | 289 | Accepted | 2
4 | 1 | 3F-757 Housing |  | 0 | 460 | Accepted | 2
5 | 1 | 8H-1247 Seal support |  | 0 | 308 | Accepted | 2
6 | 1 | Rear shaft |  | 0 | 429 | Accepted | 2
7 | 2 | Main gear |  | 0 | 537 | Accepted | 2
8 | 2 | Secondary gear |  | 0 | 320 | Accepted | 2
9 | 2 | 3F-757 Housing |  | 0 | 303 | Accepted | 1
10 | 2 | 8H-1247 Seal support |  | 0 | 506 | Accepted | 1

## tasks
Task ID | Job ID | Task Name | Task Setup Time | Task Cycle Time | Job Quantity | Task Runtime | Machine Family | Machine ID | Predecessors Task ID | Comments
3 | 1 | J1 Task 1 |  |  |  | 53 | TW | 0 | 2
1 | 1 | J1 Task 2 |  |  |  | 21 | TW | 1
2 | 1 | J1 Task 3 |  |  |  | 34 | CNC | 2 | 1
4 | 1 | J1 Task 4 |  |  |  | 55 | CNC | 3 | 3
5 | 1 | J1 Task 5 |  |  |  | 95 | LC | 4 | 4
7 | 2 | J2 Task 1 |  |  |  | 21 | TW | 0 | 6
10 | 2 | J2 Task 2 |  |  |  | 71 | TW | 1 | 9
8 | 2 | J2 Task 3 |  |  |  | 26 | CNC | 2 | 7
9 | 2 | J2 Task 4 |  |  |  | 52 | CNC | 3 | 8
6 | 2 | J2 Task 5 |  |  |  | 16 | LC | 4
11 | 3 | J3 Task 1 |  |  |  | 12 | TW | 0
14 | 3 | J3 Task 2 |  |  |  | 42 | TW | 1 | 13
12 | 3 | J3 Task 3 |  |  |  | 31 | CNC | 2 | 11
13 | 3 | J3 Task 4 |  |  |  | 39 | CNC | 3 | 12
15 | 3 | J3 Task 5 |  |  |  | 98 | LC | 4 | 14
16 | 4 | J4 Task 1 |  |  |  | 55 | TW | 0
18 | 4 | J4 Task 2 |  |  |  | 77 | TW | 1 | 17
17 | 4 | J4 Task 3 |  |  |  | 66 | CNC | 2 | 16
19 | 4 | J4 Task 4 |  |  |  | 77 | CNC | 3 | 18
20 | 4 | J4 Task 5 |  |  |  | 79 | LC | 4 | 19
25 | 5 | J5 Task 1 |  |  |  | 83 | TW | 0 | 24
21 | 5 | J5 Task 2 |  |  |  | 19 | TW | 1
24 | 5 | J5 Task 3 |  |  |  | 64 | CNC | 2 | 23
22 | 5 | J5 Task 4 |  |  |  | 34 | CNC | 3 | 21
23 | 5 | J5 Task 5 |  |  |  | 37 | LC | 4 | 22
30 | 6 | J6 Task 1 |  |  |  | 92 | TW | 0 | 29
27 | 6 | J6 Task 2 |  |  |  | 54 | TW | 1 | 26
26 | 6 | J6 Task 3 |  |  |  | 43 | CNC | 2
28 | 6 | J6 Task 4 |  |  |  | 62 | CNC | 3 | 27
29 | 6 | J6 Task 5 |  |  |  | 79 | LC | 4 | 28
35 | 7 | J7 Task 1 |  |  |  | 93 | TW | 0 | 34
33 | 7 | J7 Task 2 |  |  |  | 87 | TW | 1 | 32
34 | 7 | J7 Task 3 |  |  |  | 87 | CNC | 2 | 33
31 | 7 | J7 Task 4 |  |  |  | 69 | CNC | 3
32 | 7 | J7 Task 5 |  |  |  | 77 | LC | 4 | 31
39 | 8 | J8 Task 1 |  |  |  | 60 | TW | 0 | 38
38 | 8 | J8 Task 2 |  |  |  | 41 | TW | 1 | 37
37 | 8 | J8 Task 3 |  |  |  | 38 | CNC | 2 | 36
36 | 8 | J8 Task 4 |  |  |  | 24 | CNC | 3
40 | 8 | J8 Task 5 |  |  |  | 83 | LC | 4 | 39
43 | 9 | J9 Task 1 |  |  |  | 44 | TW | 0 | 42
44 | 9 | J9 Task 2 |  |  |  | 49 | TW | 1 | 43
45 | 9 | J9 Task 3 |  |  |  | 98 | CNC | 2 | 44
41 | 9 | J9 Task 4 |  |  |  | 17 | CNC | 3
42 | 9 | J9 Task 5 |  |  |  | 25 | LC | 4 | 41
50 | 10 | J10 Task 1 |  |  |  | 96 | TW | 0 | 49
47 | 10 | J10 Task 2 |  |  |  | 75 | TW | 1 | 46
46 | 10 | J10 Task 3 |  |  |  | 43 | CNC | 2
49 | 10 | J10 Task 4 |  |  |  | 79 | CNC | 3 | 48
48 | 10 | J10 Task 5 |  |  |  | 96 | LC | 4 | 47

## Sheet1
Job | Machine | Duration | Tasks ID | Predecessors
1 | 0 | 53 | 3 | 2
1 | 1 | 21 | 1
1 | 2 | 34 | 2 | 1
1 | 3 | 55 | 4 | 3
1 | 4 | 95 | 5 | 4
2 | 0 | 21 | 7 | 6
2 | 1 | 71 | 10 | 9
2 | 2 | 26 | 8 | 7
2 | 3 | 52 | 9 | 8
2 | 4 | 16 | 6
3 | 0 | 12 | 11
3 | 1 | 42 | 14 | 13
3 | 2 | 31 | 12 | 11
3 | 3 | 39 | 13 | 12
3 | 4 | 98 | 15 | 14
4 | 0 | 55 | 16
4 | 1 | 77 | 18 | 17
4 | 2 | 66 | 17 | 16
4 | 3 | 77 | 19 | 18
4 | 4 | 79 | 20 | 19
5 | 0 | 83 | 25 | 24
5 | 1 | 19 | 21
5 | 2 | 64 | 24 | 23
5 | 3 | 34 | 22 | 21
5 | 4 | 37 | 23 | 22
6 | 0 | 92 | 30 | 29
6 | 1 | 54 | 27 | 26
6 | 2 | 43 | 26
6 | 3 | 62 | 28 | 27
6 | 4 | 79 | 29 | 28
7 | 0 | 93 | 35 | 34
7 | 1 | 87 | 33 | 32
7 | 2 | 87 | 34 | 33
7 | 3 | 69 | 31
7 | 4 | 77 | 32 | 31
8 | 0 | 60 | 39 | 38
8 | 1 | 41 | 38 | 37
8 | 2 | 38 | 37 | 36
8 | 3 | 24 | 36
8 | 4 | 83 | 40 | 39
9 | 0 | 44 | 43 | 42
9 | 1 | 49 | 44 | 43
9 | 2 | 98 | 45 | 44
9 | 3 | 17 | 41
9 | 4 | 25 | 42 | 41
10 | 0 | 96 | 50 | 49
10 | 1 | 75 | 47 | 46
10 | 2 | 43 | 46
10 | 3 | 79 | 49 | 48
10 | 4 | 77 | 48 | 47